HATANA INNOVATION BOOTCAMP – SEF 2.0

| Project Title | ONGERA UBEHO -Youth & Family Mentorship Hub |
| --- | --- |
| Tagline | Reconnecting youth, healing families, rebuilding futures |
| Sector | Mental Health ¦ Youth Livelihoods ¦ Social Welfare |
| Target Beneficiaries | Youth aged 12–25 affected by addiction, peer pressure, or homelessness; families in Rwanda |
| Grant Requested | USD 5,000 |
| SDG Alignment | SDG 3 (Good Health), SDG 10 (Reduced Inequalities), SDG 16 (Peace, Justice & Strong Institutions) |
| Rwanda Alignment | NST2 Priority: Human Capital Development & Social Protection ¦ Vision 2050 |

# 1. THE PROBLEM

## 1.1 What Is Happening in Rwanda Today?

Across Rwanda, a growing number of children and young people are leaving their homes and ending up on the streets, under bridges, and in unsafe environments. This crisis has multiple interconnected causes:

- Substance abuse and drug addiction pulling youth away from their families

- Gambling addiction, particularly among young men aged 15–25, leading to financial ruin and family breakdown

- Peer pressure and negative social influence causing young people to drop out of school or disengage from their communities

- Family conflict, poverty, and lack of communication driving youth to abandon home

- Street children with no shelter, no food, and no guidance — invisible to support systems

Even in families with enough income, parents often feel powerless. They do not know how to communicate with their children, how to recognize early warning signs of addiction, or where to go for help. There is no structured, affordable, community-based mentorship system available to them.

## 1.2 Why Current Solutions Are Failing

- Professional counseling services are expensive and inaccessible for most Rwandan families

- Street children have no pathway to rehabilitation — they are overlooked by existing programs

- Parents have nowhere to share their problems or receive practical guidance

- There is no platform connecting concerned families with trained mentors in their language and context

## 1.3 Who Suffers Most?

The most affected groups are: (1) youth aged 12–25 from both low-income and middle-income households, (2) parents and caregivers who feel lost and unsupported, and (3) street children who have completely fallen through the cracks of society.

# 2. OUR SOLUTION: ONGERA UBEHO HUB

## 2.1 What Is ONGERA UBEHO?

INZIRA (meaning 'The Path' in Kinyarwanda) is a community-based Youth and Family Mentorship Hub that combines a physical safe space with a simple digital platform to connect struggling youth, street children, and worried parents with trained mentors and community support networks.

INZIRA operates on a two-track model:

## Track 1 – Family Mentorship Platform (For Parents & Youth at Home)

- Parents register through a simple mobile platform (accessible via basic smartphone or USSD for low-tech access)

- Parents describe their child's situation: type of problem (addiction, peer pressure, withdrawal), severity, and history

- The platform matches them with a trained peer mentor or counselor who speaks Kinyarwanda and understands local context

- Mentorship sessions happen in-person in the community, by phone call, or through WhatsApp groups — no internet required beyond basic SMS

- Parents pay a small, sliding-scale contribution (e.g., 2,000–5,000 RWF/month) to sustain the platform; low-income families are subsidized

## Track 2 – Street Youth Rehabilitation Program (For Youth Without Homes)

- ONGERA UBEHO identifies street children (ages 12–25) living under bridges and in unsafe areas of Kigali and nearby towns

- A community outreach team visits weekly to build trust and offer basic support (food, hygiene, first aid)

- Youth who express willingness are enrolled in a structured mentorship program at a designated safe space (rented community room or partnered facility)

- Mentorship covers: life skills, vocational awareness, family reintegration, and psychosocial support

- For youth who cannot be reunited with family, ONGERA UBEHO connects them to existing government-backed shelters and NGO partners

## 2.2 Why This Works in Rwanda

- Rwandans trust community-based, face-to-face interaction more than apps alone — ONGERA UBEHO is built on human connection first

- USSD/SMS integration means the platform works even on basic phones without data

- Mentors speak Kinyarwanda and are from the same communities — no cultural gap

- The dual-track model addresses BOTH ends of the crisis: families at risk AND those already on the street

# 3. EXPECTED SOCIAL IMPACT

## 3.1 Direct Beneficiaries in First 6 Months

With USD 5,000 in seed funding, ONGERA UBEHO will achieve the following within the first six months of operation:

| Beneficiary Group | Target Number | Key Outcome |
| --- | --- | --- |
| Youth at home (addiction/peer pressure) | 50 youth | Active mentorship & family reconnection |
| Street children enrolled in rehabilitation | 30 youth | Safe space, food, life skills, referral |
| Parents & caregivers supported | 40 families | Guidance, early intervention, reduced crisis |
| Community mentors trained | 10 mentors | Employment + capacity building |

## 3.2 Women & Youth Inclusion

- At least 60% of youth beneficiaries will be young women and girls — who are often hidden victims of peer pressure and family breakdown

- Female mentors will be recruited and trained, providing income and professional development

- Girls who are pregnant or with children living on the street will receive targeted support

- All platform interactions are available in Kinyarwanda, ensuring rural and low-literacy women are not excluded

# 4. BUDGET PLAN (USD 5,000)

| Mentor Training Workshop (10 mentors, 2-day) | $600 |
| --- | --- |
| Platform Development – Basic USSD/WhatsApp integration | $1,200 |
| Street Youth Outreach (transport, food, hygiene supplies – 6 months) | $1,200 |
| Community Safe Space Rental (6 months) | $700 |
| Awareness Campaign (community radio, flyers, local mobilization) | $500 |
| Operations & Coordination (team transport, communications) | $500 |
| Monitoring & Evaluation Tools | $300 |
| TOTAL | USD 5,000 |

# 5. INNOVATION & SCALABILITY

## 5.1 What Makes ONGERA UBEHO Different?

- No existing platform in Rwanda connects parents directly to community mentors for youth behavioral crises in Kinyarwanda

- ONGERA UBEHO is the only initiative that explicitly links family-based mentorship with street youth rehabilitation under one umbrella

- USSD/SMS access ensures no one is excluded by poverty or lack of smartphone

- The sliding-scale payment model creates financial sustainability without excluding the most vulnerable

## 5.2 How Will ONGERA UBEHO Grow After the Pilot?

- Revenue from paying families will subsidize free services for street youth

- After 6 months, ONGERA UBEHO will apply for partnership with MINISANTE (Ministry of Health) and MIGEPROF (Ministry of Gender) for integration into national programs

- The mentor training model can be replicated in any Rwandan district with minimal cost

- Long-term: expand to university campuses to address mental health crisis among students

# 6. HATANA ALIGNMENT CHECKLIST

| HATANA Criterion | Status |
| --- | --- |
| Clear, visible local problem in Rwanda | YES |
| Youth are direct beneficiaries (not just users) | YES |
| Women and girls clearly benefit or lead | YES |
| Low-income / rural users are not excluded | YES |
| Technology is simple and offline-friendly (USSD/SMS) | YES |
| Can be prototyped with USD 5,000 | YES |
| Focused on prevention and early intervention | YES |
| Addresses health & mental well-being | YES |
| Aligns with SDGs and Rwanda NST2 | YES |
| Community-based, not purely digital | YES |
| Culturally relevant and in Kinyarwanda | YES |

# 7. CLOSING STATEMENT

Rwanda's youth are its greatest asset. But today, thousands of young people are slipping away — into addiction, into the streets, into silence — because their families have nowhere to turn and no one to guide them.

ONGERA UBEHO does not pretend to solve all of Rwanda's social challenges. But it does something powerful and urgent: it creates a pathway — between parent and child, between street and safety, between despair and dignity.

With USD 5,000, ONGERA UBEHO will reach over 120 direct beneficiaries in six months. With the HATANA platform behind it, ONGERA UBEHO will grow into a national model that any district can replicate.

We believe every young Rwandan deserves a path forward.